## README
Enrollment & Outcomes Analytics - Requirements Workbook (baseline v1.0)
Built in Steps 2-3 of the project plan. Companion to BRD v1.0 and FRD v1.0. All data is synthetic (seeded generator: data/generate_data.py, extract v1.0).
Sheets in this version
Data Model - tables, grain, keys and Tableau relationships
Data Dictionary - every column: type, meaning, allowed values, nulls, distinct count (profiled from the extract)
Data Mapping - source column to Tableau field, with role, transformation, validation and null handling
Reconciliation - expected counts from the extract; enter Tableau values in the blue cells and Match? checks them
User Stories - 28 baseline stories with Given/When/Then acceptance criteria, linked to BR and FR
KPI Definitions - KPI-01 to KPI-10: definition, Tableau formula, rule and reference value
Ref Field & Cohort, Ref Channel & Year, Ref College - independently computed values to check Tableau against
Added in later steps
LOD Lab reference values (Step 5); Change Request log and funding/aid fields (Step 6, CR-001); Traceability and Test Cases (Step 7)
Legend
Blue font = cell for you to fill in. Status columns have dropdowns.

## Data Model
Table | Grain | Primary key | Foreign key(s) | Rows | Notes
dim_college | One row per college | college_id | - | 30 | Hub table for all relationships
fact_applications | One row per application (applicant x college x year) | application_id | college_id | 92555 | Admissions funnel and discovery channel
fact_students | One row per enrolled student (new entrant) | student_id | college_id; application_id (lineage only) | 23121 | Enrollment status and outcomes; discovery_channel copied from the application
Tableau relationships (Data Source tab, Relationships model)
Left | Right | Cardinality
dim_college.college_id | fact_applications.college_id | One to many
dim_college.college_id | fact_students.college_id | One to many
Design note
Students and applications are not related to each other in Tableau (that would create a cycle with dim_college). Channel-versus-outcome analysis uses discovery_channel stored on fact_students; application_id is kept for lineage.

## Data Dictionary
Table | Column | Data type | Description | Allowed values / rule | Nulls allowed | Actual nulls | Distinct values | Example | Origin
dim_college | college_id | Text | Unique college identifier (C01-C30) | Primary key | No | 0 | 30 | C01 | Baseline
dim_college | college_name | Text | Fictional college name | No real institutions | No | 0 | 30 | Alder Institute | Baseline
dim_college | state | Text | U.S. state postal code of the college location |  | No | 0 | 18 | PA | Baseline
dim_college | region | Text | Region of the college: Northeast, Midwest, South, West |  | No | 0 | 4 | Northeast | Baseline
dim_college | control_type | Text | Institution ownership | Public / Private Nonprofit / Private For-Profit | No | 0 | 3 | Private For-Profit | Baseline
dim_college | size_tier | Text | Size band from average annual application volume | Small / Medium / Large | No | 0 | 3 | Large | Baseline
dim_college | selectivity_tier | Text | Selectivity band from base admit rate | Highly Selective / Moderately Selective / Open Admission | No | 0 | 3 | Open Admission | Baseline
fact_applications | application_id | Text | Unique application identifier (A000001 onward) | Primary key | No | 0 | 92555 | A000001 | Baseline
fact_applications | college_id | Text | College applied to | Foreign key to dim_college | No | 0 | 30 | C01 | Baseline
fact_applications | application_year | Whole number | Fall entry year applied for (equals cohort_year if enrolled) | 2018-2025 | No | 0 | 8 | 2018 | Baseline
fact_applications | discovery_channel | Text | How the applicant first learned about the college (self-reported, one per applicant) | 8 values | No | 0 | 8 | Campus Visit / Open House | Baseline
fact_applications | applicant_state | Text | Applicant home state (postal code) |  | No | 0 | 20 | PA | Baseline
fact_applications | intended_field | Text | Field of study the applicant intended at application | 10 values | No | 0 | 10 | Physical Sciences & Math | Baseline
fact_applications | admitted_flag | Whole number | 1 if the applicant was admitted, else 0 | 0 or 1 | No | 0 | 2 | 1 | Baseline
fact_applications | enrolled_flag | Whole number | 1 if the admitted applicant enrolled, else 0 | 0 or 1; 1 only when admitted_flag = 1 | No | 0 | 2 | 0 | Baseline
fact_students | student_id | Text | Unique student identifier (S000001 onward) | Primary key | No | 0 | 23121 | S000001 | Baseline
fact_students | application_id | Text | Application that produced this student | Lineage key; unique | No | 0 | 23121 | A000018 | Baseline
fact_students | discovery_channel | Text | Channel copied from the application (denormalized) | 8 values | No | 0 | 8 | College Website | Baseline
fact_students | college_id | Text | College attended | Foreign key to dim_college | No | 0 | 30 | C01 | Baseline
fact_students | cohort_year | Whole number | Fall entry year of the student | 2018-2025 | No | 0 | 8 | 2018 | Baseline
fact_students | field_of_study | Text | Field of study at enrollment (can differ from intended_field) | 10 values | No | 0 | 10 | Arts & Humanities | Baseline
fact_students | stem_flag | Text | STEM or Non-STEM, derived from field_of_study | STEM / Non-STEM | No | 0 | 2 | Non-STEM | Baseline
fact_students | family_income_band | Text | Household income band | 5 bands | No | 0 | 5 | Under $30K | Baseline
fact_students | first_gen_flag | Whole number | 1 if first-generation college student | 0 or 1 | No | 0 | 2 | 0 | Baseline
fact_students | in_state_flag | Whole number | 1 if applicant state equals college state | 0 or 1 | No | 0 | 2 | 0 | Baseline
fact_students | hs_gpa | Decimal | High-school GPA at entry | 2.00-4.00 | No | 0 | 199 | 2.92 | Baseline
fact_students | enrollment_status | Text | Status as of 2026-08-31 | Graduated / Dropped Out / Enrolled (Active) | No | 0 | 3 | Dropped Out | Baseline
fact_students | graduation_year | Whole number (nullable) | Year of graduation (events dated May of that year) | Null unless Graduated | Yes | 14423 | 5 | 2022 | Baseline
fact_students | dropout_year | Whole number (nullable) | Year the student left without a degree | Null unless Dropped Out | Yes | 17195 | 8 | 2019 | Baseline
fact_students | years_to_outcome | Whole number (nullable) | Years from entry to graduation or dropout | Null when Enrolled (Active) | Yes | 8497 | 6 | 1 | Baseline
fact_students | cumulative_gpa | Decimal | Cumulative GPA at outcome or as-of date | 0.50-4.00 | No | 0 | 315 | 1.63 | Baseline

## Data Mapping
Source table | Source column | Tableau field name | Tableau data type | Role | Transformation / rule | Validation | Null handling | Status
dim_college | college_id | College ID | String | Dimension | None | Not null; unique | Not expected | Not started
dim_college | college_name | College | String | Dimension | None | Not null | Not expected | Not started
dim_college | state | State | String (geo role) | Dimension | Assign geographic role State/Province | Valid U.S. state postal code | Excluded from map only | Not started
dim_college | region | Region | String | Dimension | None | Not null | Not expected | Not started
dim_college | control_type | Control Type | String | Dimension | None | Not null | Not expected | Not started
dim_college | size_tier | Size Tier | String | Dimension | None | Not null | Not expected | Not started
dim_college | selectivity_tier | Selectivity Tier | String | Dimension | None | Not null | Not expected | Not started
fact_applications | application_id | Application ID | String | Dimension | None | Not null; unique | Not expected | Not started
fact_applications | college_id | College ID | String | Dimension | None | Not null; unique | Not expected | Not started
fact_applications | application_year | Application Year | Number (whole) | Dimension | Convert to Dimension (discrete) | 2018-2025 | n/a | Not started
fact_applications | discovery_channel | Discovery Channel | String | Dimension | None | One of 8 allowed values | Not expected | Not started
fact_applications | applicant_state | Applicant State | String (geo role) | Dimension | Assign geographic role State/Province | Valid postal code | Excluded from map only | Not started
fact_applications | intended_field | Intended Field | String | Dimension | None | Not null | Not expected | Not started
fact_applications | admitted_flag | Admitted Flag | Number (whole) | Measure | Leave as Measure (SUM gives admits) | 0 or 1 | Not expected | Not started
fact_applications | enrolled_flag | Enrolled Flag | Number (whole) | Measure | Leave as Measure (SUM gives enrollments) | 0 or 1; 1 only if admitted | Not expected | Not started
fact_students | student_id | Student ID | String | Dimension | None | Not null; unique | Not expected | Not started
fact_students | application_id | Application ID | String | Dimension | None | Unique; lineage only | Not expected | Not started
fact_students | discovery_channel | Discovery Channel | String | Dimension | None | One of 8 allowed values | Not expected | Not started
fact_students | college_id | College ID | String | Dimension | None | Not null; unique | Not expected | Not started
fact_students | cohort_year | Cohort Year | Number (whole) | Dimension | Convert to Dimension (discrete) | 2018-2025; drives Completed Cohort rule | Not expected | Not started
fact_students | field_of_study | Field of Study | String | Dimension | None | Not null | Not expected | Not started
fact_students | stem_flag | STEM Flag | String | Dimension | None | Not null | Not expected | Not started
fact_students | family_income_band | Family Income Band | String | Dimension | None | Not null | Not expected | Not started
fact_students | first_gen_flag | First-Gen Flag | Number (whole) | Measure | None | Not null | Not expected | Not started
fact_students | in_state_flag | In-State Flag | Number (whole) | Measure | None | Not null | Not expected | Not started
fact_students | hs_gpa | HS GPA | Number (decimal) | Measure | Number (decimal), 2 places | 2.00-4.00 | Not expected | Not started
fact_students | enrollment_status | Enrollment Status | String | Dimension | None (values used as-is) | One of 3 allowed values | Not expected | Not started
fact_students | graduation_year | Graduation Year | Number (whole) | Dimension | Convert to Dimension; keep as whole number | Null unless status = Graduated | Nulls expected for non-graduates | Not started
fact_students | dropout_year | Dropout Year | Number (whole) | Dimension | Convert to Dimension; keep as whole number | Null unless status = Dropped Out | Nulls expected for non-dropouts | Not started
fact_students | years_to_outcome | Years to Outcome | Number (whole) | Dimension | Convert to Dimension (discrete) for cohort-survival view | 1-6; null when Active | Nulls expected for active students | Not started
fact_students | cumulative_gpa | Cumulative GPA | Number (decimal) | Measure | Number (decimal), 2 places | 0.50-4.00 | Not expected | Not started
(derived) | - | Is Graduate | Number (whole) | Measure | IF [Enrollment Status] = "Graduated" THEN 1 ELSE 0 END | Result is 0 or 1 | n/a | Not started
(derived) | - | Is Dropout | Number (whole) | Measure | IF [Enrollment Status] = "Dropped Out" THEN 1 ELSE 0 END | Result is 0 or 1 | n/a | Not started
(derived) | - | Is Active | Number (whole) | Measure | IF [Enrollment Status] = "Enrolled (Active)" THEN 1 ELSE 0 END | Is Graduate + Is Dropout + Is Active = 1 | n/a | Not started
(derived) | - | Completed Cohort | Boolean | Dimension | [Cohort Year] <= [Last Complete Cohort] (parameter, default 2020) | TRUE for cohorts 2018-2020 at default | n/a | Not started
(derived) | - | Last Complete Cohort | Parameter (integer) | Parameter | Default 2020; range 2018-2025 | Drives Completed Cohort | n/a | Not started
(derived) | - | Completed Student | Number (whole) | Measure | IF [Completed Cohort] THEN 1 ELSE 0 END | 0 or 1 | n/a | Not started
(derived) | - | Completed Graduate | Number (whole) | Measure | IF [Completed Cohort] THEN [Is Graduate] ELSE 0 END | 0 or 1 | n/a | Not started
(derived) | - | Completed Dropout | Number (whole) | Measure | IF [Completed Cohort] THEN [Is Dropout] ELSE 0 END | 0 or 1 | n/a | Not started
(derived) | - | FY Dropout | Number (whole) | Measure | IF [Is Dropout] = 1 AND [Years to Outcome] = 1 THEN 1 ELSE 0 END | 0 or 1 | n/a | Not started
(derived) | - | Completed FY Dropout | Number (whole) | Measure | IF [Completed Cohort] THEN [FY Dropout] ELSE 0 END | 0 or 1 | n/a | Not started
(derived) | - | Completed GPA Sum | Number (decimal) | Measure | IF [Completed Cohort] THEN [Cumulative GPA] ELSE 0 END | Sum / Completed Student = Avg GPA | n/a | Not started

## Reconciliation
ID | Check | Table | Expected (from extract) | Tableau actual (enter) | Match? | How to check in Tableau
REC-01 | Colleges loaded | dim_college | 30 |  |  | Row count of dim_college (Number of Records)
REC-02 | Applications loaded | fact_applications | 92555 |  |  | Number of Records for fact_applications
REC-03 | Enrolled students loaded | fact_students | 23121 |  |  | Number of Records for fact_students
REC-04 | Applications with enrolled_flag = 1 equals student rows | fact_applications | 23121 |  |  | SUM of Enrolled Flag
REC-05 | Admitted applications | fact_applications | 64347 |  |  | SUM of Admitted Flag
REC-06 | Students with status Graduated | fact_students | 8698 |  |  | Count of Student ID, filter Enrollment Status
REC-07 | Students with status Dropped Out | fact_students | 5926 |  |  | Count of Student ID, filter Enrollment Status
REC-08 | Students with status Enrolled (Active) | fact_students | 8497 |  |  | Count of Student ID, filter Enrollment Status
REC-09 | Duplicate student_id values | fact_students | 0 |  |  | Count of Student ID minus Count Distinct of Student ID
REC-10 | Distinct colleges appearing in students | fact_students | 30 |  |  | Count Distinct of College ID (students)
REC-11 | Students in completed cohorts (2018-2020) | fact_students | 7898 |  |  | Count of Student ID, Cohort Year <= 2020
REC-12 | Active students inside completed cohorts | fact_students | 0 |  |  | Count of Student ID, Cohort Year <= 2020, status Active
REC-13 | Distinct discovery channels | fact_applications | 8 |  |  | Count Distinct of Discovery Channel
REC-14 | Distinct fields of study | fact_students | 10 |  |  | Count Distinct of Field of Study
REC-15 | Distinct cohort years | fact_students | 8 |  |  | Count Distinct of Cohort Year
REC-16 | Enrolled applications not admitted (should be 0) | fact_applications | 0 |  |  | Filter Enrolled Flag = 1 and Admitted Flag = 0
REC-17 | Graduation Year nulls equal non-graduates | fact_students | 14423 |  |  | Count of records where Graduation Year is Null
Tie-out
| Graduated + Dropped Out + Active minus student rows (expected 0) |  | 0
| Checks passed / entered |  | 0 / 0

## User Stories
ID | Epic | As a (persona) | I want to | So that | Priority | Acceptance criteria | Linked BR | Linked FR | Build step | Origin | Status
US-01 | E1 Admissions and discovery | VP Enrollment Management | I want to see the funnel from applications to admits to enrollments by discovery channel | So that I can see where applicants drop out of the funnel | Must | Given the Admissions dashboard, When I view the funnel, Then applications, admitted and enrolled counts are shown for each of the 8 channels. And totals equal KPI-01 and KPI-04 when no filter is applied. | BR-01 | FR-05 | Step 4 | Baseline | Not started
US-02 | E1 Admissions and discovery | VP Enrollment Management | I want to rank channels by yield rate with application volume visible | So that I recruit through channels that convert, not only channels that bring volume | Must | Given the channel ranking, When it loads, Then channels are sorted by Yield Rate (enrolled / admitted) descending. And the top channel equals the reference value in the workbook. | BR-01 | FR-06 | Step 4 | Baseline | Not started
US-03 | E1 Admissions and discovery | VP Enrollment Management | I want to see how channel mix changes by application year | So that I can spot growing channels such as social media | Should | Given the mix view, When I read it, Then each year shows channel share of applications summing to 100%. | BR-01 | FR-07 | Step 4 | Baseline | Not started
US-04 | E1 Admissions and discovery | Institutional Research Director | I want to see enrollment by cohort year split by control type | So that I understand enrollment trend by institution type | Must | Given the enrollment view, When it loads, Then enrolled students by cohort year are shown by control type. And the sum across years equals KPI-04. | BR-02 | FR-08 | Step 4 | Baseline | Not started
US-05 | E1 Admissions and discovery | Institutional Research Director | I want to filter enrollment to one college | So that I can review a single college in detail | Should | Given the College filter or a click on a college, When applied, Then enrollment and KPI tiles update for that college only. | BR-02 | FR-08, FR-18 | Step 4 | Baseline | Not started
US-06 | E2 Outcomes and performance | Academic Dean | I want to see graduated, dropped out and active share by cohort | So that I understand how each cohort is progressing | Must | Given the status view, When I read a cohort, Then Graduated, Dropped Out and Active shares sum to 100%. And cohorts 2018-2020 show 0 active students. | BR-03 | FR-09 | Step 4 | Baseline | Not started
US-07 | E2 Outcomes and performance | Academic Dean | I want to rank fields of study by graduation rate and dropout rate | So that I can compare departments on a fair basis | Must | Given the field ranking, When it loads, Then all 10 fields are ranked using completed cohorts only. And values match the Ref Field sheet. | BR-04 | FR-10 | Step 4 | Baseline | Not started
US-08 | E2 Outcomes and performance | Academic Dean | I want to see the highest and lowest fields clearly flagged | So that I can spot strong and at-risk fields immediately | Must | Given the field ranking, When I view it, Then the highest graduation field and the highest dropout field are visibly highlighted with a legend. | BR-04 | FR-10 | Step 4 | Baseline | Not started
US-09 | E2 Outcomes and performance | Student Success Lead | I want to see when students leave (year of dropout) | So that I can time retention support | Could | Given the time-to-dropout view, When I read it, Then dropouts are counted by Years to Outcome and sum to the dropout total. | BR-03 | FR-11 | Step 4 | Baseline | Not started
US-10 | E2 Outcomes and performance | Institutional Research Director | I want to rank colleges on the Performance Index with its three components | So that I can see which colleges perform best and why | Must | Given the college ranking, When it loads, Then all 30 colleges show Index, Graduation Rate, First-Year Retention and Avg GPA. And values match the Ref College sheet. | BR-05 | FR-12 | Step 4 | Baseline | Not started
US-11 | E2 Outcomes and performance | VP Enrollment Management | I want to see graduation rate by discovery channel | So that I can explore whether channel relates to completion | Could | Given the channel outcome view, When it loads, Then Graduation Rate (completed cohorts) is shown per channel with a caution note that differences are exploratory. | BR-01, BR-03 | FR-13 | Step 4 | Baseline | Not started
US-12 | E3 Segmentation and interaction | Academic Dean | I want to filter by control type, region, size tier and selectivity tier | So that I can compare like with like | Must | Given the global filters, When I select values, Then every view and KPI on the dashboard updates. | BR-06 | FR-17 | Step 4 | Baseline | Not started
US-13 | E3 Segmentation and interaction | Student Success Lead | I want to filter by STEM flag, first-gen flag and family income band | So that I can see outcomes for specific student groups | Should | Given the student filters, When I select a group, Then outcome views update and KPI counts reflect the group. | BR-06 | FR-17 | Step 4 | Baseline | Not started
US-14 | E3 Segmentation and interaction | Academic Dean | I want to click a field, channel or college to cross-filter other views | So that I can explore without resetting filters | Should | Given a view, When I click a mark, Then related views filter or highlight per the action table. And clicking a blank area clears the selection. | BR-04, BR-05 | FR-18 | Step 4 | Baseline | Not started
US-15 | E3 Segmentation and interaction | Business Analyst | I want to change the Last Complete Cohort parameter | So that I can see how the completed-cohort rule affects rates | Could | Given the parameter control, When I change it from 2020 to 2019, Then completed-cohort KPIs recalculate for cohorts 2018-2019. | BR-09 | FR-19 | Step 4 | Baseline | Not started
US-16 | E4 KPI governance | Institutional Research Director | I want to see KPI tiles that follow the governed definitions | So that numbers are consistent across teams | Must | Given a dashboard, When it loads with no filters, Then each KPI tile equals its reference value in the KPI Definitions sheet. | BR-07 | FR-14 | Step 4 | Baseline | Not started
US-17 | E4 KPI governance | Hiring manager | I want to open the definition of each KPI from the dashboard | So that I understand what each number means without asking | Must | Given the dashboard, When I open the info panel or hover a KPI, Then its definition and formula summary are shown. | BR-07 | FR-15 | Step 4 | Baseline | Not started
US-18 | E4 KPI governance | Hiring manager | I want to see a synthetic-data banner, the as-of date and the censoring note | So that I do not mistake the findings for real-world facts | Must | Given any dashboard, When it loads, Then the banner, as-of date 2026-08-31 and the note on recent cohorts are visible. | BR-09, BR-10 | FR-16 | Step 4 | Baseline | Not started
US-19 | E5 LOD Lab | Business Analyst | I want to compare a benchmark dropout rate from a table calculation, EXCLUDE LOD and FIXED LOD | So that I can explain how each responds to filters | Must | Given demo A, When I filter Control Type, Then the table-calculation and EXCLUDE benchmarks change while the FIXED benchmark does not. And values match the reference values. | BR-08 | FR-20 | Step 5 | Baseline | Not started
US-20 | E5 LOD Lab | Business Analyst | I want to compare percent of total as a table calculation and as a FIXED LOD | So that I can explain why shares sum to 100% in one and not the other | Must | Given demo B with Control Type = Public, When I read the shares, Then the table-calculation shares sum to 100% and the LOD shares sum to the public share of all students. | BR-08 | FR-21 | Step 5 | Baseline | Not started
US-21 | E5 LOD Lab | Business Analyst | I want to compare a pooled graduation rate with the average of college rates | So that I can show how weighting changes a KPI | Must | Given demo C, When I compare values, Then pooled and average-of-college graduation rates are shown overall and by field with the difference in points. | BR-08 | FR-22 | Step 5 | Baseline | Not started
US-22 | E5 LOD Lab | Business Analyst | I want to compare a FIXED LOD under a normal filter and under a context filter | So that I can explain the order of operations | Must | Given demo D, When I move Control Type to context, Then the FIXED benchmark changes to the filtered population. | BR-08 | FR-23 | Step 5 | Baseline | Not started
US-23 | E5 LOD Lab | Hiring manager | I want to read annotations with the expected values for each demo | So that I can verify the lab is correct | Should | Given the lab dashboard, When I read an annotation, Then it states the filter setting and the expected values. | BR-08 | FR-24 | Step 5 | Baseline | Not started
US-24 | E6 Delivery | Hiring manager | I want to open the dashboard from a public link without logging in | So that I can review the work quickly | Must | Given the Tableau Public URL, When I open it in a supported browser, Then it loads in 5 seconds or less without login. | BR-10 | FR-25 | Step 8 | Baseline | Not started
US-25 | E6 Delivery | Color-blind viewer | I want to use a palette I can distinguish | So that I can read every chart accurately | Should | Given a color-blind simulation, When I view the dashboards, Then categories remain distinguishable and meaning does not depend on color alone. | BR-10 | FR-26 | Step 8 | Baseline | Not started
US-26 | E7 Data preparation | Business Analyst | I want to work from a typed, related data source with correct geographic roles | So that calculations and maps are reliable | Must | Given the three CSV files, When the data source is set up, Then relationships use college_id, State has a geographic role and year fields are dimensions. | BR-09 | FR-01, FR-02 | Step 4 | Baseline | Not started
US-27 | E7 Data preparation | Business Analyst | I want to have helper flags and the Completed Cohort rule | So that every KPI is a simple, auditable ratio of sums | Must | Given the helper fields, When I test them, Then Is Graduate + Is Dropout + Is Active = 1 for every student and Completed Cohort is TRUE only for cohorts 2018-2020 at the default parameter. | BR-03, BR-09 | FR-03 | Step 4 | Baseline | Not started
US-28 | E7 Data preparation | Business Analyst | I want to reconcile Tableau counts to the Reconciliation sheet | So that I can prove the data loaded correctly | Must | Given the Reconciliation sheet, When I enter Tableau values, Then all 17 checks show OK. | BR-09 | FR-04 | Step 4 | Baseline | Not started

## KPI Definitions
ID | KPI | Business definition | Tableau formula | Source table | Rule / filter | Reference value (no filters) | Origin
KPI-01 | Total Applications | Number of applications received | COUNT([Application ID]) | fact_applications | None | 92555 | Baseline
KPI-02 | Admit Rate | Admitted applications divided by applications | SUM([Admitted Flag]) / COUNT([Application ID]) | fact_applications | None | 69.52% | Baseline
KPI-03 | Yield Rate | Enrolled divided by admitted (BRU-06) | SUM([Enrolled Flag]) / SUM([Admitted Flag]) | fact_applications | None | 35.93% | Baseline
KPI-04 | Enrolled Students | Number of new entrants | COUNT([Student ID]) | fact_students | None | 23121 | Baseline
KPI-05 | Graduation Rate (6-yr) | Graduates divided by students, completed cohorts | SUM([Completed Graduate]) / SUM([Completed Student]) | fact_students | Cohort Year <= Last Complete Cohort (2020) | 70.54% | Baseline
KPI-06 | Dropout Rate (completed cohorts) | Dropouts divided by students, completed cohorts | SUM([Completed Dropout]) / SUM([Completed Student]) | fact_students | Completed cohorts | 29.46% | Baseline
KPI-07 | Attrition to Date | Dropouts divided by all students, all cohorts (BRU-04) | SUM([Is Dropout]) / COUNT([Student ID]) | fact_students | All cohorts; active students in denominator | 25.63% | Baseline
KPI-08 | First-Year Retention | 1 minus first-year dropout share, completed cohorts (BRU-08) | 1 - SUM([Completed FY Dropout]) / SUM([Completed Student]) | fact_students | Completed cohorts | 87.01% | Baseline
KPI-09 | College Performance Index | Weighted index of graduation, retention and GPA per college (BRU-07) | 100 * (0.60 * [Graduation Rate] + 0.25 * [First-Year Retention] + 0.15 * [Avg GPA] / 4) | fact_students | Per college; completed cohorts | Top 83.3; bottom 60.6; see Ref College | Baseline
KPI-10 | Top Channel by Yield | Channel with the highest yield rate | Sort channels by [Yield Rate] descending | fact_applications | None | Campus Visit / Open House (53.1%) | Baseline
KPI-11 onward are reserved for approved future changes so existing IDs never change.

## Ref Field & Cohort
Field of study (rates on completed cohorts 2018-2020; attrition to date on all cohorts)
Rank by graduation | Field of study | Students (all cohorts) | Students (completed cohorts) | Graduation rate (6-yr) | Dropout rate (completed) | Attrition to date
1 | Nursing & Health Sciences | 3247 | 1137 | 79.33% | 20.67% | 16.6%
2 | Education | 1862 | 665 | 75.34% | 24.66% | 22.07%
3 | Business | 3454 | 1173 | 72.98% | 27.02% | 23.6%
4 | Biology & Life Sciences | 2074 | 684 | 71.78% | 28.22% | 24.11%
5 | Psychology | 1998 | 663 | 70.29% | 29.71% | 27.23%
6 | Engineering | 2295 | 803 | 69.86% | 30.14% | 26.19%
7 | Computer Science | 2632 | 884 | 67.42% | 32.58% | 28.46%
8 | Physical Sciences & Math | 1360 | 462 | 66.02% | 33.98% | 28.68%
9 | Social Sciences | 1914 | 664 | 63.86% | 36.14% | 31.82%
10 | Arts & Humanities | 2285 | 763 | 61.47% | 38.53% | 33.61%
Status by cohort year
Cohort year | Graduated | Dropped Out | Enrolled (Active) | Total | Graduated share | Dropped Out share | Active share
2018 | 1807 | 796 | 0 | 2603 | 69.42% | 30.58% | 0%
2019 | 1931 | 778 | 0 | 2709 | 71.28% | 28.72% | 0%
2020 | 1833 | 753 | 0 | 2586 | 70.88% | 29.12% | 0%
2021 | 1826 | 837 | 177 | 2840 | 64.3% | 29.47% | 6.232%
2022 | 1301 | 874 | 809 | 2984 | 43.6% | 29.29% | 27.11%
2023 | 0 | 840 | 2158 | 2998 | 0% | 28.02% | 71.98%
2024 | 0 | 676 | 2471 | 3147 | 0% | 21.48% | 78.52%
2025 | 0 | 372 | 2882 | 3254 | 0% | 11.43% | 88.57%

## Ref Channel & Year
Discovery channel (ranked by yield rate; graduation rate on completed cohorts)
Rank by yield | Channel | Applications | Admitted | Enrolled | Admit rate | Yield rate | Share of enrolled | Graduation rate (6-yr)
1 | Campus Visit / Open House | 12573 | 9063 | 4811 | 72.08% | 53.08% | 20.81% | 72.19%
2 | Friends / Family / Alumni | 12450 | 8579 | 4027 | 68.91% | 46.94% | 17.42% | 68.55%
3 | High School Counselor | 14266 | 9844 | 3927 | 69% | 39.89% | 16.98% | 71.68%
4 | College Website | 19608 | 13584 | 4494 | 69.28% | 33.08% | 19.44% | 71.05%
5 | College Fair | 7133 | 4951 | 1535 | 69.41% | 31% | 6.639% | 68.29%
6 | Online Search / Rankings Sites | 8875 | 6206 | 1654 | 69.93% | 26.65% | 7.154% | 70.86%
7 | Social Media | 13725 | 9437 | 2152 | 68.76% | 22.8% | 9.308% | 69.78%
8 | Advertising / Direct Mail | 3925 | 2683 | 521 | 68.36% | 19.42% | 2.253% | 67.14%
Application year
Year | Applications | Admitted | Enrolled | Admit rate | Yield rate | Social Media share of applications
2018 | 10469 | 7301 | 2603 | 69.74% | 35.65% | 8.243%
2019 | 10857 | 7503 | 2709 | 69.11% | 36.11% | 9.984%
2020 | 10233 | 7124 | 2586 | 69.62% | 36.3% | 11.9%
2021 | 11433 | 7927 | 2840 | 69.33% | 35.83% | 13.46%
2022 | 11924 | 8274 | 2984 | 69.39% | 36.06% | 15.55%
2023 | 12059 | 8374 | 2998 | 69.44% | 35.8% | 17.43%
2024 | 12642 | 8805 | 3147 | 69.65% | 35.74% | 18.93%
2025 | 12938 | 9039 | 3254 | 69.86% | 36% | 20.65%

## Ref College
College Performance Index (completed cohorts 2018-2020; weights 0.60 / 0.25 / 0.15)
Rank | College ID | College | Control type | Region | Students (completed) | Graduation rate | First-year retention | Avg GPA | Performance Index
1 | C21 | University of Upland | Private Nonprofit | Midwest | 78 | 83.33% | 89.74% | 2.8935 | 83.2864
2 | C11 | University of Kestrel | Private Nonprofit | South | 317 | 82.02% | 92.11% | 2.9236 | 83.2034
3 | C20 | Timberline College | Private Nonprofit | Northeast | 251 | 81.67% | 90.84% | 2.9514 | 82.7809
4 | C15 | Oakhurst College | Private Nonprofit | Midwest | 289 | 79.93% | 92.04% | 2.8949 | 81.8249
5 | C03 | Cedar Ridge State University | Public | West | 396 | 78.54% | 91.67% | 2.866 | 80.7855
6 | C28 | Copperfield State University | Public | Midwest | 112 | 77.68% | 91.96% | 2.9071 | 80.4997
7 | C02 | Brookhaven College | Private Nonprofit | Northeast | 145 | 75.86% | 89.66% | 2.9336 | 78.932
8 | C06 | University of Fairhaven | Private Nonprofit | South | 173 | 75.72% | 89.6% | 2.8563 | 78.5435
9 | C30 | Elmhurst State University | Public | West | 139 | 75.54% | 88.49% | 2.8458 | 78.1176
10 | C23 | Westbrook College | Private Nonprofit | Northeast | 102 | 72.55% | 94.12% | 2.8888 | 77.8919
11 | C29 | Driftwood College | Private Nonprofit | South | 504 | 75.4% | 87.7% | 2.853 | 77.8613
12 | C08 | Harborview College | Private Nonprofit | Midwest | 240 | 74.17% | 88.75% | 2.8301 | 77.3003
13 | C16 | Pinecrest State University | Public | West | 198 | 72.73% | 89.9% | 2.8231 | 76.6977
14 | C25 | Zephyr Bay State University | Public | Midwest | 410 | 72.44% | 87.56% | 2.8464 | 76.0275
15 | C18 | Redwater College | Private Nonprofit | West | 267 | 71.91% | 88.01% | 2.8542 | 75.8529
16 | C10 | Juniper Falls State University | Public | South | 427 | 71.9% | 89.23% | 2.7689 | 75.8284
17 | C22 | Valemont State University | Public | Northeast | 291 | 71.48% | 85.57% | 2.8123 | 74.8246
18 | C12 | Lakemont College | Private Nonprofit | Midwest | 101 | 67.33% | 88.12% | 2.9068 | 73.3264
19 | C07 | Glenmoor State University | Public | Midwest | 388 | 68.81% | 84.54% | 2.8647 | 73.1652
20 | C14 | Northfield State University | Public | South | 252 | 68.65% | 84.92% | 2.8373 | 73.0604
21 | C19 | University of Stonebridge | Private Nonprofit | West | 213 | 68.54% | 84.98% | 2.8277 | 72.9746
22 | C13 | Maplewood State University | Public | South | 316 | 66.14% | 86.08% | 2.7993 | 71.6998
23 | C27 | Briarwood Institute | Private For-Profit | West | 235 | 64.68% | 84.68% | 2.7899 | 70.4407
24 | C04 | Dunmore Institute | Private For-Profit | Midwest | 213 | 64.32% | 83.1% | 2.7725 | 69.7632
25 | C05 | Eastgate Institute | Private For-Profit | Midwest | 582 | 63.4% | 85.4% | 2.7367 | 69.6528
26 | C01 | Alder Institute | Private For-Profit | Northeast | 375 | 63.47% | 84.27% | 2.7447 | 69.4395
27 | C17 | Quarry Hill State University | Public | West | 210 | 63.33% | 84.29% | 2.7401 | 69.3468
28 | C26 | Ashford State University | Public | Midwest | 246 | 61.79% | 81.71% | 2.8292 | 68.1096
29 | C09 | Ironwood Institute | Private For-Profit | Northeast | 268 | 58.96% | 80.97% | 2.7418 | 65.8975
30 | C24 | Yarrow Institute | Private For-Profit | South | 160 | 52.5% | 75.62% | 2.714 | 60.5838