ENROLLMENT TO GRADUATION

Change Request Pack

U.S. College Enrollment & Outcomes Analytics

| Baseline | BRD v1.0, FRD v1.0, requirements workbook v1.0 (git tag baseline-v1.0) |
| --- | --- |
| Requests in this pack | CR-001 Funding and Scholarships module (Approved); CR-002 Transfer-out status (Deferred); CR-003 Live data refresh (Rejected) |
| Resulting version | v1.1 (BRD, FRD, workbook, data extract, Tableau addendum) |
| Prepared by | Nida Khan, Business Analyst |

Simulated engagement. Requesters, approvers and dates are illustrative (dated by project week) to demonstrate a real change-control process.

# 1. Change Control Process

| # | Stage | What happens | Owner |
| --- | --- | --- | --- |
| 1 | Raise | Anyone submits a CR describing the change and why it is needed | Requester |
| 2 | Log | BA assigns an ID and records it in the CR log | BA |
| 3 | Triage | BA checks the request is clear, not a duplicate and not already in scope | BA |
| 4 | Impact analysis | BA assesses scope, requirements, data, design, effort, schedule, risk, testing and documents | BA |
| 5 | Decision | Change Control Board decides: Approve, Approve with conditions, Defer or Reject | Sponsor + BA |
| 6 | Implement | Work is done on a separate git branch; affected documents are updated | BA / Developer |
| 7 | Verify | Regression: baseline KPIs must be unchanged; new requirements tested | BA |
| 8 | Re-baseline | Version numbers increase, revision history is updated, release is tagged in git | BA |

Versioning: an approved CR that adds scope raises the minor version (v1.0 to v1.1). A change that redefines existing KPIs or statuses raises the major version (v2.0). Requirement, KPI, story and test IDs are never reused or renumbered.

## Git traceability

| Item | Convention | CR-001 example |
| --- | --- | --- |
| Branch | cr-<id>-<short-name> | cr-001-funding-scholarships |
| Pull request | Title starts with the CR ID; description is the CR summary and impact table | CR-001: Add funding and scholarships module |
| Tag | Baseline or release after merge | v1.1 |
| Deferred / rejected | No branch; recorded in this pack and the CR log | CR-002, CR-003 |

# 2. CR-001: Add Funding and Scholarships Module

| CR ID / Title | CR-001 - Add Funding and Scholarships module |
| --- | --- |
| Requested by | Director of Financial Aid (simulated), via Executive Sponsor |
| Raised | Project week 3 (after baseline sign-off) |
| Type / Priority | Scope addition / High |
| Status | APPROVED with conditions |
| Version affected | v1.0 to v1.1 |

## 2.1 Description of change

Add analysis of student scholarships and aid, college funding and scholarship budget utilization, and the relationship between aid coverage and graduation. This adds student aid fields, a college funding table at college and fiscal-year level, five KPIs, one dashboard and one LOD Lab demo.

## 2.2 Business justification

- The Financial Aid Office cannot currently see whether scholarship spending relates to student outcomes.

- Funding data sits at a different level of detail from student data, which adds a real-world LOD example (double counting) to the lab.

- Completes the original topic: enrollment, admissions, funding, scholarships, graduation and dropout.

## 2.3 Baseline versus proposed

| Item | Baseline v1.0 | Proposed v1.1 |
| --- | --- | --- |
| Business requirements | BR-01 to BR-10 | Adds BR-11 (aid analysis), BR-12 (funding and utilization), BR-13 (aid vs outcomes) |
| Functional requirements | FR-01 to FR-26 | Adds FR-27 to FR-34 |
| KPIs | KPI-01 to KPI-10 | Adds KPI-11 to KPI-15; KPI-01 to KPI-10 unchanged |
| User stories | 28 | Adds 10 (US-29 to US-38) |
| Data tables | 3 (30 + 92,555 + 23,121 rows) | 4: adds fact_college_funding (240 rows) |
| fact_students columns | 16 | 22: adds tuition, scholarship type and amount, grant, loan, net cost |
| Dashboards | 3 | 4: adds Aid and Funding; Lab gains demo E |
| LOD Lab demos | 4 (A to D) | 5 (adds E: fan-out from mixed grain) |

## 2.4 Impact analysis

| Area | Impact | Level |
| --- | --- | --- |
| Scope | Adds one module; no removal of baseline scope | Medium |
| Requirements | 3 BR, 8 FR, 5 KPI, 10 user stories, new business rules BRU-10 to BRU-12 | Medium |
| Data | New table at college-year level; 6 new student columns; one new relationship; extract v1.1 generated by the same seeded script so shared values are identical | Medium |
| Design | One new dashboard (about 6 sheets); Dashboard 3 gains one demo | Medium |
| Existing KPIs | No definition changes. Regression test required to confirm KPI-01 to KPI-10 are unchanged | Low |
| Testing | New test cases for FR-27 to FR-34 plus a full regression run | Medium |
| Documents | BRD, FRD and workbook to v1.1; Tableau addendum; README; CR log | Medium |

## 2.5 Effort and schedule

| Work | Person-days |
| --- | --- |
| Requirements and document updates | 1.0 |
| Data extract v1.1, dictionary and mapping, reconciliation | 0.5 |
| Tableau build: Dashboard 4 and demo E | 2.0 |
| Testing and regression | 0.5 |
| Total | 4.0 |

Schedule impact: about one extra week in the Build phase. Cost impact: none (portfolio project).

## 2.6 Risks introduced

| ID | Risk | Mitigation |
| --- | --- | --- |
| RSK-06 | Mixed grain: joining funding (college-year) to students duplicates funding values and inflates totals | Use relationships; add demo E with expected values; reconciliation checks on funding totals |
| RSK-07 | Baseline KPIs change unintentionally when new tables are added | Mandatory regression test against reference values; extract v1.1 keeps all shared values identical |
| RSK-08 | Further scope requests follow | Keep CR-002 and CR-003 on record; hold the line on v1.1 scope |

## 2.7 Options considered

| Option | Description | Assessment |
| --- | --- | --- |
| A | Defer to a later release | No effort now; the original topic stays incomplete and no mixed-grain example |
| B | Student-level aid only (no funding table) | About 2 days; misses budget utilization and funding per student; no fan-out demo |
| C | Full module (recommended) | About 4 days; completes topic; adds demo E; manageable risk with regression test |

## 2.8 Decision

| Decision | Approved (Option C) with conditions |
| --- | --- |
| Conditions | 1. Regression test passes: KPI-01 to KPI-10 identical to baseline. 2. Funding totals reconcile (REC checks). 3. v1.0 documents remain in the repository next to v1.1. |
| Decided | Project week 3 (Change Control Board) |

| Name | Role | Decision | Signature / date |
| --- | --- | --- | --- |
|  | Executive Sponsor (simulated) | Approve |  |
|  | Director of Financial Aid (simulated) | Consulted |  |
| Nida Khan | Business Analyst / CCB secretary | Recommend approval |  |

## 2.9 Affected artifacts

| Artifact | From | To | Change |
| --- | --- | --- | --- |
| BRD | v1.0 | v1.1 | Revision history, scope, stakeholders, BR-11 to BR-13, objectives, risks |
| FRD | v1.0 | v1.1 | New data, rules, KPIs 11-15, FR-27 to FR-34, Dashboard 4, demo E |
| Requirements workbook | v1.0 | v1.1 | Dictionary, mapping, reconciliation, stories, KPIs, references, traceability, test cases, CR log |
| Data extract | v1.0 | v1.1 | fact_students +6 columns; fact_college_funding added |
| Tableau guide | v1.0 | Addendum | Part E: funding data, Dashboard 4, demo E, regression checks |

# 3. CR-002: Add Transferred-Out Student Status

| CR ID / Title | CR-002 - Add "Transferred Out" as an enrollment status |
| --- | --- |
| Requested by | Student Success Lead (simulated) |
| Raised | Project week 3 |
| Type / Priority | Definition change / Medium |
| Status | DEFERRED to v2.0 |

## 3.1 Description and justification

Some students who leave a college transfer to another institution and are not dropouts. Treating them as dropouts overstates attrition. The request is to add a fourth status, Transferred Out, and decide how it is treated in rates.

## 3.2 Impact analysis

| Area | Impact | Level |
| --- | --- | --- |
| Business rules | BRU-02 changes from 3 statuses to 4; a rule is needed for whether transfers stay in the graduation denominator | High |
| KPIs | KPI-05 to KPI-08 change definition; every reference value changes | High |
| Data | Outcome generation changes, so shared values are no longer identical across versions; all reconciliation counts change | High |
| Dashboards | Status, field, college and Lab views need rebuilding and revalidating | High |
| Effort / schedule | About 6 person-days and a full retest | High |
| Risk | Invalidates the validated baseline (regression cannot pass by design) | High |

## 3.3 Decision

Deferred to v2.0. It is a redefinition, not an addition, so it needs a major version and a sponsor decision on how transfers are treated. It would also break the v1.1 condition that baseline KPIs stay unchanged. Revisit when there is capacity for a full re-baseline.

# 4. CR-003: Live or Scheduled Data Refresh

| CR ID / Title | CR-003 - Live or scheduled refresh of the data |
| --- | --- |
| Requested by | VP Enrollment Management (simulated) |
| Raised | Project week 4 |
| Type / Priority | Scope addition / Low |
| Status | REJECTED |

Reason: the data is a static synthetic snapshot, so there is nothing to refresh, and a Tableau Public workbook built on CSV files cannot be scheduled to refresh. Out of scope per BRD section 5.2.

# 5. Change Request Log

| ID | Title | Requester | Raised | Type | Priority | Status | Version | Effort (days) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CR-001 | Funding and scholarships module | Financial Aid Director | Week 3 | Scope addition | High | Approved | v1.1 | 4.0 |
| CR-002 | Transferred-out status | Student Success Lead | Week 3 | Definition change | Medium | Deferred | v2.0 | 6.0 (est.) |
| CR-003 | Live data refresh | VP Enrollment Mgmt | Week 4 | Scope addition | Low | Rejected | - | n/a |